## Introduction
Resource Name | Ateeb Adil
Mentor | Shayesta Maqsood
Joining Date | 2022-01-03
Review 1
Review 2
Review 3

## Training Task
Project Name
S.No. | Area | Priority | Screen | Training Task | Estimate
0 | Orientation |  |  | Read orientation email. | 2:55 hrs
|  |  |  | Read about Git. | 1:15 hrs
|  |  |  | Read SQA tutorials | 7 hrs | Start Date | 2022-01-03
|  |  |  | Activate repository in the system | 1 hrs | End Date | 2022-01-05
|  |  |  | Set up outlook and transfer outlook data file to D drive | 1 hrs | Effort (Working Days) | 2
1 | Software Concepts |  |  | To understand about types of testing i.e., Functional testing, UI/UX testing, Performance testing, Penetration testing, Database testing, Regressiont esting, end to end testing | 3 hrs | Start Date | 2022-01-05
|  |  |  | To understand about bug prioirty and severity and bug life cycle on mantis | 3 hrs | End Date | 2022-01-05
|  |  |  | Read and document basic concept on following topics: 1. Html5 compliance 2. SSL 3. Sessions, cookies & cache 4. Web request / response lifecycle 5. MVC Concepts 6. Hashing 7. Dialogs 8. Webservers and app servers. 9. Multi language support and localization. | 2 hrs | Effort (Working Days) | 1
2 | Database |  |  | Setup and installation for SQL Server. | 30 min | Start Date | 2022-01-05
|  |  |  | Perform the basic database operations. Make a sheet of your query and attach the screenshot of your output. Insert, delete, update, where clause, joins and etc. | 3 days | End Date
3 | Understanding of the project |  |  | Read and undestand the requirement document of the timesheet project. |  | Effort (Working Days)
Make a query sheet and raise queries.
|  |  |  | Make a brief presentation of what you have understood regarding the project. | N/A
|  |  |  | Present the presentation, fix and update the suggested changes | N/A
4 | Deployment |  |  | Deploy the timesheet project release |  | Start Date
|  |  |  | Resolve and troubleshoot the issues faced in the deployment. |  | End Date
|  |  |  | Create a deployment guide of your project. |  | Effort (Working Days)
5 | Functional Testing |  | User Management Screen | Analyze the requirements and create test cases. |  | Start Date
|  |  |  | Get the test cases reviewed by mentor, update test cases if required according to feedback |  | End Date
|  |  |  | Execute test cases |  | Effort (Working Days)
Bug Reporting
Create testing summary report.
6 | Functional Testing |  | Manage Project | Analyze the requirements and create test cases. |  | Start Date
|  |  |  | Get the test cases reviewed by mentor, update test cases if required according to feedback |  | End Date
|  |  |  | Execute test cases |  | Effort (Working Days)
Bug reporting
Testing summary
7 | Review feedback |  |  | Work on review feedback